## Sheet1
TABELLA DEI FUNCTION POINTS
FUNCTION POINTS |  |  | Valore
F1 | Data Communications |  | 4
F2 | Distrib. Data Processing |  | 0
F3 | Performance |  | 1
F4 | Heavily Used Configuration |  | 0 |  | m = | RELY * DATA * CPL * TIME *
F5 | Transaction Rate |  | 1 |  |  | * STCQ * VIRT * TURN * ACAP
F6 | Online Data Entry |  | 5 |  |  | * AEXP * PCAP * VEXP * LEXP
F7 | End User Efficiency |  | 0 |  |  | * MOOD * TOOL * SCED *
F8 | Online Update |  | 0
F9 | Complex Processing |  | 2 |  | m = | B * N * B* N *
F10 | Reusability |  | 4 |  |  | * - * B * A * B *
F11 | Insatallation Ease |  | 0 |  |  | * N * N * N * N
F12 | Operational Ease |  | 0 |  |  | * N * A
F13 | Multiple sites |  | 0
F14 | Facilitate Changes |  | 3 |  | m = | 0,88 * 1 * 0,85* 1 *
* - * 0,87 * 1,07 * 1,19 *
* 1 * 1 * 1 * 1 *
DI | 20 |  |  |  |  | * 1 * 1 * 1,04
[5 empty] | m = | 0.86
TCF = | 0,65 x 0,01 x 20
TCF = | 0.85
Function Points = UFP X TCF
|  | Input | 28
|  | Output | 8
|  | File Logico | 11
|  | Interfaccia Esterna | 0
|  | Interrogazioni Esterne | 0
PESI
| basso |  | 28 x 3 = | 84
| basso e medio |  | (6x4) + (2x5) = | 34
| medio e basso |  | 11 x 7 = | 77
|  | UFP | 195
|  | TCF |  | 0.85
|  | FP = UFP X TCF |  | 165.75
|  | Dimensioni = KDSLOC |  | 99.45
| Effort | PM = 2.4 (KDSI)1.05 M
|  | PM | 258.3418 | persone/mese
Time Development
|  | TDEV | 20.6336 | mesi
Personale Richiesto
|  | N = Effort/TDEV = | 12.5205 | persone
|  | Effort= A x KDSLOC^B x m | 258.3418
|  | TDEV = C x Effort^0,38 | 20.6336
|  | N= Effort /TDEV | 12.5205
Effort
| PM | 258.3418 | persone/mese
|  | Time Development |  | approssimazione
| TDEV | 20.6336 | mesi | 20 | mesi ==> | 19 giorni
[5 empty] | = | 152 | ore
Personale Richiesto
| N = Effort/TDEV = | 12.5205 | persone |  | Costo Orario | 8 | euro
Costo Sistema = persone x ore x Costo orario (8 euro)
| Costo Sistema = |  | 25090.3995 | euro | costo a persona
|  |  | 15224.8945 | euro | costo mensile